# Governed Prompt Gateway Business Requirements

Two month delivery baseline  |  Retail banking support  |  Version 1.0

# Purpose and business outcome

Build and demonstrate a governed control layer that processes customer-service prompts before an LLM is used. The prototype must reduce unsafe model access and estimated cost while producing an auditable record of every decision. It is a project demonstration, not a production banking system or legal compliance certification.

| Business objective | Success measure |
| --- | --- |
| Improve safety | At least 80 percent F1 for prompt-risk classification, with precision and recall reported on public and banking-specific test sets. |
| Reduce model usage | Blocked and valid cached prompts do not reach a generation model. |
| Reduce input cost | Report token reduction for eligible prompts; retain the original 30 to 50 percent target as an aspiration, not a release gate. |
| Improve auditability | One complete decision record for every query, including blocked and cached queries. |

# Scope

| In scope | Out of scope |
| --- | --- |
| Retail banking queries; text cleanup; personal-data masking; risk classification; ALLOW, BLOCK, or ESCALATE policy; semantic cache; simple model-tier routing; token and cost estimates; audit record; Streamlit demo. | Production deployment; live customer data or bank integration; legal advice or compliance certification; large-scale paid model calls; jurisdiction-specific profiles; complex prompt optimization; full automated testing product. |

# Minimum functional requirements

| ID | Requirement | Acceptance evidence |
| --- | --- | --- |
| FR 01 | A Python interface accepts a query and returns a disposition, response, and JSON decision record. | One command processes the evaluation workload end to end. |
| FR 02 | Personal account and card patterns are masked before classification, caching, routing, and logging. | Privacy tests show no raw detected values downstream. |
| FR 03 | A lightweight classifier labels toxic, jailbreak, harmful, and regulated-advice risk. | Metrics reported on public and banking-specific test sets. |
| FR 04 | Versioned policy rules return ALLOW, BLOCK, or ESCALATE with a reason. | Demo includes every outcome; BLOCK and ESCALATE stop execution. |
| FR 05 | Eligible allowed prompts use semantic cache lookup with a threshold and intent-based time-to-live rule. | Hit rate, precision, recall, and selected threshold reported. |
| FR 06 | Allowed cache misses receive a simple model-tier recommendation and estimated cost. | Tier distribution and governed-versus-baseline cost shown. |
| FR 07 | The dashboard shows stage results, risk, cache status, tier, tokens, and estimated savings. | Single-query and aggregate views work in the demo. |
| FR 08 | Every request records policy, model, configuration, threshold, and outcome versions where applicable. | Audit record count equals processed query count. |

# Eight week delivery plan

| Week | Committed outcome | Exit condition |
| --- | --- | --- |
| 1 | Agree on schema, scope, risk taxonomy, dataset versions, and evaluation split. Build a basic pipeline shell. | One query produces a complete placeholder decision record. |
| 2 | Load and profile ToxicChat and Banking77. Add token counts, privacy masking, keyword baseline, and policy rules. | Baseline pipeline runs over a small workload. |
| 3 | Train or fine-tune the lightweight risk classifier. Draft the banking attack set. | Baseline and candidate metrics recorded. |
| 4 | Finalize safety evaluation and policy configuration. Freeze the attack evaluation set. | Public and banking-specific safety results approved internally. |
| 5 | Build semantic cache, threshold sweep, and cache time-to-live table. | Cache precision and recall curve produced. |
| 6 | Add simple intent-based routing, cost model, and full workload runner. | Estimated savings and tier distribution produced. |
| 7 | Complete Streamlit views, documentation, architecture diagram, and limitations. | Feature complete and code frozen at week end. |
| 8 | Fix demonstration defects, rehearse, and finalize results and presentation. No new features. | Repeatable demo and final repository ready. |

# Deliverables and acceptance

| Deliverable | Minimum acceptance condition |
| --- | --- |
| Python package | Stable processing interface and versioned policy configuration. |
| Streamlit application | Shows all stages for one query and aggregate workload results. |
| Evaluation results | Safety, cache, token, routing, and estimated cost metrics with documented assumptions. |
| Repository documentation | Setup, usage, architecture, datasets, decisions, limitations, and demo script. |

# Delivery priorities and cuts

Protect: end-to-end integration, decision records, easy-versus-hard safety evaluation, privacy masking, cache precision and recall, and the governed-versus-baseline cost comparison.

Cut first: prompt compression, advanced complexity routing, extra datasets, jurisdiction profiles, and automated test-harness features. If routing slips, route by intent. If model training slips, ship the strongest evaluated baseline and document the limitation.

# Key risks and controls

| Risk | Control |
| --- | --- |
| Classifier learns topic instead of harmfulness | Report public and banking-specific results separately. |
| Incorrect or stale cache reuse | Optimize for precision; use thresholds, intent labels, time-to-live rules, and never-cache categories. |
| Sensitive data reaches logs or cache | Mask before downstream stages and inspect every output surface. |
| Schedule expansion | Freeze features after week 7 and apply the stated cut order. |
| Estimated savings are overstated | Publish price assumptions and label simulated costs clearly. |

# Decisions required in week one

Advisor approves retail banking scope and the lightweight classifier approach.

Team approves the decision-record schema, risk taxonomy, and ALLOW, BLOCK, or ESCALATE rules.

Team defines ToxicChat label use, the held-out banking attack set, and cache policies for Banking77 intents.

Cost team documents model tiers, prices, and the all-highest-tier comparison baseline.

Approval status  Working baseline pending advisor and team confirmation.